## Apprentice Student Jun'19
Training plan for MTE30 Apprentice Student Jun - Jul '19
Name: MR.PATCHARAWAT SUKRUK From: Chiang Mai University Major: Computer Engineering
| Theme Date | Trainer / Supporter | Jun'19 | [29 empty] | Jul'19
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
General | 1. Orientation program | MTA30 / MTA20 | bar: Jun'19 3
| 2. E30 overall | Mr.Piyawat | bar: Jun'19 3
| 3. Introduction | Mr.Piyawat | bar: Jun'19 3
| 3.1) MTL organization | Mr.Piyawat | bar: Jun'19 3
| 3.2) Working rule & culture | Mr.Piyawat | bar: Jun'19 3
| 4. Transfer the Project | Mr.Piyawat | bar: Jul'19 23 to Jul'19 26
| 5. Final Presentation | Mr.Piyawat | bar: Jul'19 30
Learning | 1. Basic IoT System | Mr.Pongpitch | bar: Jun'19 4
| 2. Electrical wiring | Mr.Piyawat | bar: Jun'19 4
| 3. Basic Computer Programming (Arduino) | Mr.Piyawat | bar: Jun'19 5
| 4. Electronics & Hardware Using (Arduino Kit) | Mr.Piyawat | bar: Jun'19 5
| 5. Raspberry PI | Mr.Piyawat | bar: Jun'19 6 to Jun'19 7
| 6. Dashboard & Monitoring System | Mr.Piyawat | bar: Jun'19 7
Project | Smart Training Room Part I (Monitoring Training Room Zone 2)
| 1. Concept Design | Mr.Piyawat | bar: Jun'19 10
| 2. Hardware & Electronics Design | Mr.Piyawat | bar: Jun'19 10 to Jun'19 11
| 3. Electrical Circuit Design | Mr.Nutdanai | bar: Jun'19 11
| 4. Test & Debug & Coding | Mr.Piyawat | bar: Jun'19 11 to Jun'19 14; Jun'19 24 to Jun'19 26
| 5. Wiring Circuit | Mr.Nutdanai | bar: Jun'19 17 to Jun'19 19
| 6. Cover Circuit | Mr.Nutdanai / Mr.Piyawat | bar: Jun'19 19 to Jun'19 21
| 7. Install in Training Room | Mr.Nutdanai / Mr.Piyawat | bar: Jun'19 24
| 8. Check Error Training Room | E30 Team | bar: Jun'19 24 to Jun'19 27
9. Part I Present | bar: Jun'19 28
Smart Training Room Part II (Automatic Room Model)
| 1. Concept Design | Mr.Piyawat | bar: Jun'19 28
| 2. Hardware & Electronics Design | Mr.Nutdanai | bar: Jul'19 1
| 3. Electrical Circuit Design | Mr.Nutdanai | bar: Jul'19 2 to Jul'19 4
| 4. Test & Debug & Coding | Mr.Nutdanai | bar: Jul'19 3 to Jul'19 5; Jul'19 8 to Jul'19 11
| 5. Wiring Circuit | Mr.Nutdanai | bar: Jul'19 11 to Jul'19 12; Jul'19 17 to Jul'19 18
| 6. Cover Circuit | Mr.Nutdanai / Mr.Piyawat | bar: Jul'19 18 to Jul'19 20
| 7. Install in Training Room | E30 Team | bar: Jul'19 22
| 8. Check Error Training Room | E30 Team | bar: Jul'19 22 to Jul'19 26
Install in Training Room
Job description (Sort by Priority)
Job function
Maintenance IoT
KPI
1. Study or learning about Maintenance IoT
2. Apply Knowledge about IoT
2.1) Project Smart Training Room Part 1
(Monitoring Training Room 2nd Zone 2)
2.2) Support Project Smart Training Room Part 2
(Automatic Training Room 2nd Zone 2)
Target
Finish 100%
Finish 100%
100% Achieve Plan